## Team Efforts
Application Type | Application | Category | App Category/Integration | Activities/Task | Daily/Weekly/Monthly | Duration in /Hours (Onshore) | Duration in /Hours/Per Day (Onshore) | Duration in /Hours (Offshore) | Duration in /Hours/Per Day (Offshore)
ZG | CRDR | Operations | CRDR Operations | CRDR Refresh | Daily | 0.5 | 0.5 | 3 | 3
ZG | CRDR | Operations | CRDR Onshore/Offshore Connect | CRDR Team meeting | Daily | 0.5 | 0.5 | 0.5 | 0.5
ZG | CRDR | Operations | CRDR (Web-UI) | Incident/Service Request & Change managemant | Daily | 1 | 1 | 3 | 3
ZG | CRDR | Operations | CRDR -Meetings | CRDR -Meetings | Daily | 1 | 1 | 0.5 | 0.5
ZG | DIAL | Operations | AIRFLOW Monitoring (Weekday+ Weekends) | Airflow Job Monitoring (ODM/DIAL) | Daily | 3 | 3 | 5 | 5
ZG | DIAL | Operations | DIAL-SO Operations | SO, Liaison /Databricks Connection update | Quarterly | 8 | 0.088889 | 0 | 0
ZG | DIAL | Operations | ODM-Operations | Operational Activity for ODM applications (Incidents/Request) | Daily | 1 | 2 | 4 | 4
ZG | DIAL | Operations | DIAL - SOP Activity | Report generation for DIAL | Daily | 0 | 0 | 1 | 1
ZG | DIAL | Operations | DIAL-Meeting(SIP/CTRRPR/CS/AS/SMART) | ODM Daily Scrum call | Daily | 0 | 0 | 0 | 0
ZG | DIAL | Enhancement/Release | DIAL Releases | DIAL Release (SIP/CTRRPR/CS/AS/SMART) | Daily | 8 | 8 | 20 | 20
ZG | DIAL | Operations | DIAL-Operations | Operational Activity for production issues(SMART/SIP/CTRRPR/SO/CS-AS/B2P/BIOTRACKS)+Meetings | Daily | 1 | 1 | 0 | 0
ZG | DIAL | Operations | ODM/DIAL-Operations | Daily Meetings Onshore/Offshore Connect | Daily | 1 | 1 | 1 | 1
ZG | DIAL | Operations | DIAL-CS/AS-MuleSoft | Operational Activity - Health Check, Monitoring | Daily | 1 | 1 | 0 | 0
ZG | DIAL | Operations | DIAL- CS/AS Mulesoft | Operation activity for Wave Migration post production issues | Daily | 0 | 0 | 0 | 0
ZG | DIAL | Operations | DIAL - Vault Clinical Mulesoft | Operational Activity - Health Check, Monitoring | Daily | 0.5 | 0.5 | 1 | 1
ZG | DIAL | Operations | DIAL- Vault Clinical Mulesoft | Operation activity for Wave Migration post production issues | Daily | 0 | 0 | 0 | 0
ZG | DIAL | Bug Fix | DIAL -Vault Clinical | Bug fix release to accommodate Wave 1 Migration | Daily | 4 | 4 | 6 | 6
ZG | DIAL | Operations | ODM-DIAL | Adhoc Meetings with Business Team | Monthly | 5 | 0.16667 | 2 | 0.066667
ZG | DIAL | Operations | Knowledge Transfer for Product to Support | KT meetings for different Zero Gravity applications | Ad-Hoc | 5 | 0.013699 | 5 | 0.013699
ZG | DIAL | Operations | Knowledge Transfer within support teams | KT meetings within support for better understanding and fill-in the gaps | Ad-Hoc | 5 | 0.013699 | 5 | 0.013699
ZG | DIAL | Operations | MuleSoft AS/CS | Operational Activity (Incidents/Request) | Daily | 1.5 | 1.5 | 1.5 | 1.5
ZG | DIAL | Operations | Mulesoft B2P | Operational Activity - Health Check, Monitoring | Daily | 1.5 | 1.5 | 3 | 3
ZG | DIAL | Operations | Mulesoft SMART | Operational activity - Health Check, Monitoring | Daily | 0.5 | 0.5 | 1 | 1
ZG | OTID | Operations | OTID | Operational Activity (Incidents/Request) | Daily | 3 | 3 | 28 | 28
ZG | OTID | Operations | OTID | Infom Trial Open & Monitoring /Email notification | Weekly | 4 | 0.57143 | 4 | 0.57143
ZG | OTID | Operations | OTID | Proactive Daily Monitoring for OTID Provisioning | Daily | 0.5 | 0.5 | 3 | 3
ZG | OTID | Operations | OTID | Ad-hoc OTID Future Enhancement Meeting | Weekly | 2 | 0.28571 | 0 | 0
ZG | OTID | Operations | OTID | OTID call with BPMOPS | Weekly | 2 | 0.28571 | 1 | 0.14286
ZG | OTID | Operations | OTID | OTID call with Business Team/Hypercare | Weekly | 3 | 0.42857 | 1 | 0.14286
ZG | OTID | Operations | OTID | OTID adhoc meetings with other downstream systems (Veeva Clinical/Vault Quality/ OTID Factory Team) | Weekly | 3 | 0.42857 | 2 | 0.28571
ZG | OTID | Operations | OTID | OTID knowledge Transfer from Factory to support team | Monthly | 4 | 0.13333 | 2 | 0.066667
ZG | OTID | Operations | OTID | Certification Renewal(Vault Quality->OTID(Mulesoft),Vault Clinical->OTID(Mulesoft), Legacy InForm->OTID(Mulesoft) | Yearly | 2 | 0.0054795 | 5 | 0.013699
ZG | OTID | Operations | OTID-Datahub | Email Notification to Datahub Team for Trial opened for CLMS in OTID | Weekly | 0.5 | 0.071429 | 1 | 0.14286
ZG | OTID | Operations | OTID | Internal Team Meeting within support for better understanding and fill-in the gaps | Daily | 1 | 1 | 1 | 1
ZG | OTID | Operations | OTID-MUL | AIM MUL monitoring | Daily | 0 | 0 | 0.5 | 0.5
ZG | OTID | Operations | OTID-MUL | EISF monitoring | Weekly | 0 | 0 | 0.5 | 0.071429
ZG | OTID | Operations | OTID-MUL | MUL Monitoring | Daily | 0.5 | 0.5 | 1 | 1
ZG | OTID | Operations | OTID-MUL | Operational Activity (Incidents/Request) | Daily | 4 | 4 | 8 | 8
ZG | OTID | Operations | OTID MUL Utility -Vendor file merging | AMS to run MUL Utility to merge MUL fles for all the vendors where the frequency is set to weekly and delivery type is sharepoint (With every Wave migration Trial count will increase and hence the AMS efforts will increase) | Daily | 1 | 1 | 0 | 0
ZG | OTID | Operations | OTID MUL Utility -xml conversion | AMS to run the utility to convert the IRT vendor .xls file to .xlm file and place them on to sftp server (With every Wave migration Trial count will increase and hence the AMS efforts will increase) | Daily | 2.5 | 2.5 | 2 | 2
ZG | OTID | Operations | OTID MUL Workaround | Working with business for file correction before sending to Vendors | Daily | 2.5 | 2.5 | 0 | 0
ZG | OTID | Operations | OTID-MUL Business Meeting | Busienss Meeting | Daily | 2 | 2 | 0 | 0
Legacy | SPECTRUM-MUL | Operations | MUL | MUL dashborad report | Weekly | 0 | 0 | 1 | 0.14286
Legacy | SPECTRUM-MUL | Operations | MUL | MUL vendor report | Weekly | 0 | 0 | 0.5 | 0.071429
Legacy | SPECTRUM-MUL | Operations | MUL | Incidents/ITASK | Daily | 0 | 0 | 1.5 | 1.5
Legacy | SPECTRUM-MUL | Operations | MUL | SCTask | Daily | 0 | 0 | 6 | 6
Legacy | SPECTRUM-MUL | Operations | MUL | MUL Monitoring | Daily | 1 | 1 | 0.5 | 0.5
Legacy | SPECTRUM-MUL | Operations | MUL | MUL Meeting with BSO | Biweekly | 1 | 0.066667 | 1 | 0.066667
Legacy | SPECTRUM-MUL | Operations | MUL | Adhoc work(meeting with user) | Weekly | 1.5 | 0.21429 | 1.5 | 0.21429
Legacy | SPECTRUM-MUL | Operations | MUL | Team meeting | Daily | 0.5 | 0.5 | 0.5 | 0.5
Legacy | Spectrum I2S | Operations | I2S | Incidents/ITASK | Daily | 0.5 | 0.5 | 1.5 | 1.5
Legacy | Spectrum I2S | Operations | I2S | SCTask | Daily | 0 | 0 | 1 | 1
Legacy | Spectrum I2S | Operations | I2S | I2S monitoring | Daily | 0 | 0 | 0.5 | 0.5
Legacy | Spectrum I2S | Operations | I2S | Team meeting | Daily | 0 | 0 | 0.5 | 0.5
Legacy | SPRDR | Operations | SPRDR | Site list Report | Weekly | 0 | 0 | 0 | 0
Legacy | SPRDR | Operations | SPRDR | Monthly Monday Monitoring | Monthly | 0 | 0 | 0 | 0
Legacy | SPRDR | Operations | SPRDR | Drug & Ancillary Report | Daily | 0 | 0 | 1 | 1
Legacy | SPRDR | Operations | SPRDR | Non Person Account review Memo | Quarterly | 0 | 0 | 8 | 0.088889
Legacy | SPRDR | Operations | SPRDR | Autosys Jobs Monitoring | Daily | 0 | 0 | 2 | 2
Legacy | SPRDR | Operations | SPRDR | Incidents/sctasks/itask/Prod issues -SNOW/Email | Daily | 0 | 0 | 1 | 1
Legacy | SPRDR | Operations | SPRDR | Steep rock Query | Biweekly | 0 | 0 | 0.5 | 0.033333
Legacy | SPRDR | Operations | SPRDR | DR Acivity | Yearly | 0 | 0 | 0 | 0
Legacy | SPRDR | Operations | SPRDR | RIDE Sever Patching activity/Upgrade activity | Yearly | 0 | 0 | 0 | 0
Legacy | CORE | Operations | CORE | CORE Monitoring count | Weekly | 0 | 0 | 0.5 | 0.071429
Legacy | CORE | Operations | CORE | Provisioning & Non provisioning Report | Weekly | 0 | 0 | 2.5 | 0.35714
Legacy | CORE | Operations | CORE | CORE Monitoring | Daily | 0 | 0 | 2 | 2
Legacy | CORE | Operations | CORE | InForm Trial Migration 7.0.0.x to 7.0.x | Weekly | 0 | 0 | 3 | 0.42857
Legacy | CORE | Operations | CORE | Standard Change Request | Monthly | 0 | 0 | 5 | 0.16667
Legacy | CORE | Operations | CORE | Non Person Account review Memo | Quarterly | 0 | 0 | 3 | 0.033333
Legacy | CORE | Operations | CORE | CORE Jobs Monitoring | Daily | 0 | 0 | 0.5 | 0.5
Legacy | CORE | Operations | CORE | Incidents/sctasks/itask/Prod issues (on Email) | Daily | 0 | 0 | 8 | 8
Legacy | CORE | Operations | CORE | CORE Batch Monitoring | Monthly | 0 | 0 | 1 | 0.033333
Legacy | CORE | Operations | CORE | Data Migration Acivity for OTID | Daily | 0 | 0 | 0 | 0
Legacy | CORE | Operations | CORE | Team meeting | Daily | 0 | 0 | 1 | 1
Legacy | CORE | Operations | CORE | Adhoc Business request | Monthly | 0 | 0 | 2 | 0.066667
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM Data Weekly Monitoring | Weekly | 0 | 0 | 1 | 0.14286
Legacy | SPECTRUM | Operations | SPECTRUM | Inform to SPECTRUM and CRO to SPECTRUM Feed Load | Weekly | 0 | 0 | 2 | 0.28571
Legacy | SPECTRUM | Operations | SPECTRUM | Spectrum Monthly Account Review | Monthly | 0 | 0 | 1 | 0.033333
Legacy | SPECTRUM | Operations | SPECTRUM | Unable to find suitable Subject Template - Daily Report | Daily | 0 | 0 | 1 | 1
Legacy | SPECTRUM | Operations | SPECTRUM | SIP OUTBOUND monitoring | Daily | 0 | 0 | 0.5 | 0.5
Legacy | SPECTRUM | Operations | SPECTRUM | Aging Report Reason for Weekly Ticket | Weekly | 0 | 0 | 1 | 0.14286
Legacy | SPECTRUM | Operations | SPECTRUM | Aging daily report | Daily | 0 | 0 | 1 | 1
Legacy | SPECTRUM | Operations | SPECTRUM | Review of MRL Weekly Deck | Weekly | 0 | 0 | 1 | 0.14286
Legacy | SPECTRUM | Operations | SPECTRUM | saftey start date did not rolled up | Daily | 0 | 0 | 0.5 | 0.5
Legacy | SPECTRUM | Operations | SPECTRUM | Duplicate Site List | Daily | 0 | 0 | 0.5 | 0.5
Legacy | SPECTRUM | Operations | SPECTRUM | Position check | Daily | 0 | 0 | 0.5 | 0.5
Legacy | SPECTRUM | Operations | SPECTRUM | Batch Monitoring | Daily | 0 | 0 | 0.5 | 0.5
Legacy | SPECTRUM | Operations | SPECTRUM | SDC Ageing ticket | Weekly | 0 | 0 | 1 | 0.14286
Legacy | SPECTRUM | Operations | SPECTRUM | MRL TPR Key Highlights | Monthly | 0 | 0 | 1 | 0.033333
Legacy | SPECTRUM | Operations | SPECTRUM | ILP Data Sheet | Monthly | 0 | 0 | 1 | 0.033333
Legacy | SPECTRUM | Operations | SPECTRUM | Components monitoring | Daily | 1 | 1 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Previlaged Account Review | Yearly | 0 | 0 | 8 | 0.021918
Legacy | SPECTRUM | Operations | SPECTRUM | Downtime template | Monthly | 0 | 0 | 2 | 0.066667
Legacy | SPECTRUM | Operations | SPECTRUM | DL sync | Daily | 0 | 0 | 2 | 2
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM to SIP outbound transaction failure report | Daily | 0 | 0 | 3 | 3
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM to SIP transaction issue analysis | Weekly | 0 | 0 | 0.5 | 0.071429
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM to SIP Timeout issues analysis | Weekly | 0.5 | 0.071429 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Issues analysis/ monitoring of RCR job | Weekly | 0.5 | 0.071429 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Monthly Maintenance Activities | Monthly | 4 | 0.13333 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Shutting down the Siebel server | Monthly | 1 | 0.033333 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Starting up the Siebel servers | Monthly | 1 | 0.033333 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Release Activities | Ad-Hoc | 8 | 0.021918 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Genbscript generation | Ad-Hoc | 0.5 | 0.0013699 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | ALM script execution IQ/OQ | Ad-Hoc | 2 | 0.0054795 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Daily Health check | Daily | 1 | 1 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Siebel server components check(PROD) | Daily | 0.5 | 0.5 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Siebel Repeating Jobs check(PROD) | Daily | 0.5 | 0.5 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Siebel File system check (PROD) | Daily | 0.5 | 0.5 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Siebel Server check (UAT) | Daily | 0.5 | 0.5 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Server support(Startup/Stop/genbscript/) | Ad-Hoc | 0.5 | 0.0013699 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Siebel certificate Renewal | Yearly | 8 | 0.021918 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Siebel certificate Renewal | Yearly | 8 | 0.021918 | 0 | 0
Legacy | SPECTRUM | Operations | SPECTRUM | PRR Document | Yearly | 8 | 0.021918 | 8 | 0.021918
Legacy | SPECTRUM | Operations | SPECTRUM | DR Document Preapartion | Yearly | 8 | 0.021918 | 8 | 0.021918
Legacy | E2E | Operations | E2E | CLMS Trial deployment | Weekly | 0 | 0 | 6 | 0.85714
Legacy | E2E | Operations | E2E | InForm Trial Initiation | Weekly | 0 | 0 | 0.5 | 0.071429
Legacy | E2E | Operations | E2E | InForm Trial Deployment | Weekly | 0 | 0 | 2 | 0.28571
Legacy | E2E | Operations | E2E | InForm Email/User Termination | Weekly | 0 | 0 | 0.5 | 0.071429
Legacy | E2E | Operations | E2E | User's Queries | Daily | 2 | 2 | 1 | 1
Legacy | E2E | Operations | E2E | CLMS Quarterly Account Review | Quarterly | 0 | 0 | 6 | 0.066667
Legacy | E2E | Operations | E2E | Team Meeting | Daily | 1 | 1 | 1 | 1
Legacy | E2E | Operations | E2E | Adhoc Report | Monthly | 0 | 0 | 0.5 | 0.016667
Legacy | E2E | Operations | E2E | Incident/Service Request & Change managemant (Provisioning+Account Merging) | Daily | 2 | 2 | 26 | 26
Legacy | SPECTRUM | Operations | SPECTRUM | Team Meeting | Daily | 2 | 2 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Incidents/sctasks/itask/ | Daily | 2 | 2 | 25 | 25
Legacy | SPECTRUM | Operations | SPECTRUM | CRQ on Monthly Basis | Monthly | 2 | 0.066667 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM to Veeva Data Migration Activities | Ad-Hoc | 50 | 0.13699 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | Prod Issues by email | Daily | 4 | 4 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | SIP Provisioning/De Provisioning report | Ad-Hoc | 4 | 0.010959 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM Business Connect | Weekly | 1 | 0.14286 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM to Veeva Migration Call activity tracking | Daily | 1 | 1 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM RD Clinical Weekly status Connect | Weekly | 1 | 0.14286 |  | 0
Legacy | SPECTRUM | Operations | SPECTRUM | SPECTRUM - SIP Business Connect | Biweekly | 1 | 0.066667 |  | 0
ZG | Vault Clinical | Operations | Vault Clinical | Operational Activity(Tickets,Service Request,Itask) | Daily | 16 | 16 | 80 | 80
ZG | Vault Clinical | Operations | Vault Clinical | Meeting | Daily

## Ticket
Application | Ticket Count per Day | Ticket Count per Month
OTID | 16 | 28 | 28

## Legacy Apps effort estimation
Application | Application Task | Task Frequency (DAILY/Weekly/Biweekly/Monthly) | Offshore Resource Effort (in Hours) | Onshore Resource Effort (in Hours)
Spectum MUL | MUL dashborad report | Weekly | 1 |  | 0.14286
| MUL vendor report | weekly | 0.5
| Incidents/ITASK | Daily | 1.5
| SCTask | Daily | 6
| MUL Monitoring | Daily | 0.5 | 1
| MUL Meeting with BSO | Biweekly | 1 | 1
| Adhoc work(meeting with user) | Weekly | 1.5 | 1.5
| Team meeting | Daily | 0.5 | 0.5
Spectrum I2S | Incidents/ITASK | Daily | 1.5 | 0.5
| SCTask | Daily | 1
| I2S monitoring | Daily | 0.5
| Team meeting | Daily | 0.5
SPRDR | Site list Report | Weekly (Every Monday) | 2
| Monthly Monday Monitoring | Monthly ( 1 Monadu of the Month) | 1
| Weekly Monitoring count | Weekly
| Drug & Ancillary Report | Daily | 1
| Non Person Account review Memo | Quarterly | 8
| Autosys Jobs Monitoring | Daily | 2
| Incidents/sctasks/itask/Prod issues -SNOW/Email | Daily | 1
| Steep rock Query | Biweekly | 0.5
| DR Acivity | Yearly |  | 24
| RIDE Sever Patching activity/Upgrade activity | Yearly |  | 14
CORE | CORE Monitoring count | Weekly | 0.5
| Provisioning & Non provisioning Report | Twice in week | 2.5
| CORE Monitoring | Daily | 2
| InForm Trial Migration 7.0.0.x to 7.0.x | Weekly | 3
| Standard Change Request | Monthly | 5
| Non Person Account review Memo | Quarterly | 3
| CORE Jobs Monitoring | Daily | 0.5
| Incidents/sctasks/itask/Prod issues (on Email) | Daily | 8
| CORE Batch Monitoring | Monthly | 1
| Data Migration Acivity for OTID | Daily | 2 | 2
| Team meeting | Daily | 1
| Adhoc Business request | Monthly | 2
SPECTRUM | SPECTRUM Data Weekly Monitoring | Weekly | 1 Hours
| Inform to SPECTRUM and CRO to SPECTRUM Feed Load | Weekly | 2 Hours
| Spectrum Monthly Account Review | Monthly | 1 Hours
| Unable to find suitable Subject Template - Daily Report | Daily | 1 Hours
| SIP OUTBOUND monitoring | Daily | 30 Mins
| Aging Report Reason for Weekly Ticket | Weekly | 1 Hours
| Aging daily report | Daily | 1 Hour
| Review of MRL Weekly Deck | Weekly | 1 Hour
| saftey start date did not rolled up | Daily | 30 mins
| Duplicate Site List | Daily | 30 mins
| Position check | Daily | 30 mins
| Batch Monitoring | Daily | 30 mins
| SDC Ageing ticket | Weekly | 1 hour
| MRL TPR Key Highlights | Monthly | 1 hour
| ILP Data Sheet | Monthly | 1 hour
| Components monitoring | Daily |  | 1 hour
| Previlaged Account Review | Yearly once | 8 hours
| Downtime template | Monthly twice | 2 Hours
| DL sync | Daily | 2 Hours
| SPECTRUM to SIP outbound transaction failure report | Daily twice | 3 Hours
| SPECTRUM to SIP transaction issue analysis | Weekly | 30 mins
| SPECTRUM to SIP Timeout issues analysis | Weekly |  | 30 mins
| Issues analysis/ monitoring of RCR job | Weekly |  | 30 mins
| Monthly Maintenance Activities | Every Month |  | 4 Hours
| Shutting down the Siebel server | Every Month |  | 1 Hour
| Starting up the Siebel servers | Every Month |  | 1 Hours
| Release Activities | Ad -Hoc |  | 8 hours
| Genbscript generation | Ad- Hoc |  | 30 mins
| ALM script execution IQ/OQ | Ad- Hoc |  | 2 Hours
| Daily Health check | All working Days |  | 1 Hours
| Siebel server components check(PROD) | All working Days |  | 30 mins
| Siebel Repeating Jobs check(PROD) | All working Days |  | 30 mins
| Siebel File system check (PROD) | All working Days |  | 20 mins
| Siebel Server check (UAT) | All working Days |  | 30 mins
| Server support(Startup/Stop/genbscript/) | Ad- Hoc |  | 30 mins
| Siebel certificate Renewal | Yearly once |  | 8 Hours
| Siebel certificate Renewal | Yearly once |  | 8 hours
| PRR Document | 18 months once | 8 hours | 8 hours
| DR Document Preapartion | Yearly once | 8 hours | 8 hours