## Team Efforts
Application | Category | App Category/Integration | Activities/Task | Daily/Weekly/Monthly | Duration in /Hours (Onshore) | Duration in /Hours/Per Day (Onshore) | Duration in /Hours (Offshore) | Duration in /Hours/Per Day (Offshore)
CRDR | Operations | CRDR Operations | CRDR Refresh | Daily | 0.5 | 0.5 | 3 | 3
CRDR | Operations | CRDR (Web-UI) | Incident/Service Request & Change managemant | Daily | 1 | 1 | 1 | 1
CRDR | Operations | CRDR -Meetings | CRDR -Meetings | Daily | 1 | 1 | 0.5 | 0.5
DIAL | Operations | AIRFLOW Monitoring (Weekday+ Weekends) | Airflow Job Monitoring (ODM/DIAL) | Daily | 3 | 3 | 5 | 5
DIAL | Operations | DIAL-SO Operations | SO, Liaison /Databricks Connection update | Quarterly | 8 | 0.12 | 0 | 0
DIAL | Operations | ODM-Operations | Operational Activity for ODM applications (Incidents/Request) | Daily | 1 | 1 | 1 | 1
DIAL | Operations | DIAL-Meeting(SIP/CTRRPR/CS/AS/SMART) | ODM Daily Scrum call | Daily | 1 | 1 | 0 | 0
DIAL | Inhancement/Release | DIAL Releases | DIAL Release (SIP/CTRRPR/CS/AS/SMART) | Daily | 2 | 2 | 4 | 4
DIAL | Inhancement/Release | DIAL -CTRRPR | Impact Analysis (New Release-Veeva 2.0) | Daily | 2 | 2 | 0 | 0
DIAL | Inhancement/Release | DIAL -SIP | Impact Analysis on production issues +Follow-up meetings with downstream | Ad-Hoc | 12 | 0.5 | 6 | 0.25
DIAL | Operations | DIAL-Operations | Operational Activity for production issues for different downstream (SMART/SIP/CTRRPR/SO/CS-AS/B2P/BIOTRACKS) | Daily | 1.5 | 1.5 | 1.5 | 1.5
DIAL | Operations | ODM/DIAL-Operations | Daily Meetings Onshore/Offshore Connect | Daily | 2 | 2 | 2 | 2
DIAL | Operations | DIAL-CS/AS-MuleSoft | Operational Activity for production issues | Daily | 1 | 1 | 0 | 0
DIAL | Operations | DIAL- CS/AS Mulesoft | Operation activity for Wave 1 Migration post production issues | Daily | 7 | 7 | 7 | 7
DIAL | Operations | DIAL- Vault Clinical Mulesoft | Operation activity for Wave 1 Migration post production issues | Daily | 2 | 2 | 2 | 2
DIAL | Bug Fix | DIAL -Vault Clinical | Bug fix release to accommodate Wave 1 Migration | Daily | 4 | 4 | 6 | 6
DIAL | Operations | ODM-DIAL | Adhoc Meetings with Business Team | Monthly | 5 | 0.25 | 2 | 0.1
DIAL | Operations | Knowledge Transfer for Product to Support | KT meetings for different Zero Gravity applications | Adhoc/Monthly | 5 | 0.25 | 5 | 0.25
DIAL | Operations | Knowledge Transfer within support teams | KT meetings within support for better understanding and fill-in the gaps | Adhoc/Monthly | 5 | 0.25 | 5 | 0.25
DIAL | Operations | MuleSoft AS/CS | Operational Activity (Incidents/Request) | Daily | 1.5 | 1.5 | 1.5 | 1.5
DIAL | Operations | MuleSoft AS/CS | Transaction Monitoring Dashboard POC | ON HOLD
DIAL | Operations | Mulesoft B2P | Operational activity | Daily | 0.5 | 0.5 | 1 | 1
DIAL | Operations | Mulesoft SMART | Operational activity | Daily
OTID | Operations | OTID | Operational Activity (Incidents/Request) | Daily | 1 | 1 | 3 | 3
OTID | Operations | OTID | Proactive Daily Monitoring for OTID Provisioning | Daily | 0.5 | 0.5 | 2 | 2
OTID | Operations | OTID | Ad-hoc OTID Future Enhancement Meeting | Weekly | 1 | 0.2 | 0 | 0
OTID | Operations | OTID | OTID call with BPMOPS | Weekly | 1 | 0.2 | 0 | 0
OTID | Operations | OTID | OTID call with Business Team | Weekly | 1 | 0.2 | 0 | 0
OTID | Operations | OTID | OTID adhoc meetings with other downstream systems (Veeva Clinical/Vault Quality/ OTID Factory Team) | Weekly | 5 | 1 | 2 | 0.4
OTID | Operations | OTID | OTID knowledge Transfer from Factory to support team | Monthly (Every 2-3 months there is a release) | 2 | 0.1 | 2 | 0.1
OTID | Operations | OTID | Internal Team Meeting within support for better understanding and fill-in the gaps | Daily | 0.5 | 0.5 | 0.5 | 0.5
OTID | Operations | OTID-MUL | AIM MUL monitoring | Daily | 0.5 | 0.5 | 0.5 | 0.5
OTID | Operations | OTID MUL Utility -Vendor file merging | AMS to run MUL Utility to merge MUL fles for all the vendors where the frequency is set to weekly and delivery type is sharepoint (With every Wave migration Trial count will increase and hence the AMS efforts will increase) | Daily | 3 | 3 | 1 | 1
OTID | Operations | OTID MUL Utility -xml conversion | AMS to run the utility to convert the IRT vendor .xls file to .xlm file and place them on to sftp server (With every Wave migration Trial count will increase and hence the AMS efforts will increase) | Daily | 1.5 | 1.5 | 0 | 0
OTID | Operations | OTID MUL Workaround | Working with business for file correction before sending to Vendors | Daily | 2 | 2 | 0 | 0
OTID | Operations | OTID | Insight and observation on Incident/Service request | Daily | 2 | 2 | 2 | 2

## Pivot Table
Row Labels | Sum of Duration in /Hours/Per Day (Onshore) | Sum of Duration in /Hours/Per Day (Offshore)
DIAL | 29.87 | 31.85
OTID | 12.7 | 9.5
CRDR | 2.5 | 4.5
Grand Total | 45.07 | 45.85